## Work Order
Suryanagar Refinery, Gujarat - Maintenance Work Order
Work Order Number | WO-2026-0098
Title | P-101 Mechanical Seal Leak - Repair
Equipment Tag | P-101
Equipment Description | Centrifugal Feed Pump, Unit 2
Date Raised | 2026-02-10
Raised By | M. Iyer (Maintenance Head)
Assigned To | S. Verma (Field Technician)
Priority | Medium
Status | Completed
Completion Date | 2026-02-18
Labour Hours | 12
Linked Documents | SOP D15 (P-101 Startup Procedure); Inspection Report D13 (2026-03-05); Incident Report D19 (2026-04-15)
Problem Description
Minor mechanical seal leak observed on P-101 during routine operator rounds. Seal flush line suspected to be partially blocked, causing dry-running wear on the primary seal face. Work order raised for seal replacement and flush line inspection.
Parts / Materials Used
Mechanical seal kit (P-101 spec), seal flush line fittings, PTFE gasket set
Notes
Startup to follow SOP D15 with explicit seal flush verification step. A follow-up inspection (D13, 2026-03-05) later confirmed wear consistent with shaft misalignment rather than flush blockage alone — recommend alignment check at next planned shutdown. A minor spill incident (D19) occurred during a subsequent seal-related intervention in April.