## Work Order
Suryanagar Refinery, Gujarat - Maintenance Work Order
Work Order Number | WO-2026-0142
Title | V-204 External Shell Corrosion Repair
Equipment Tag | V-204
Equipment Description | Naphtha Storage Tank, 5000 kL capacity
Date Raised | 2026-03-14
Raised By | R. Sharma (Shift Engineer)
Assigned To | S. Verma (Field Technician)
Priority | High
Status | Completed
Completion Date | 2026-03-28
Labour Hours | 46
Linked Documents | Inspection Report D11 (2026-01-18); Hot Work Permit D14 (2026-04-05); Near-Miss Report D18 (2026-05-12); OISD-105 Audit D22 (2026-06-10)
Problem Description
Follow-up to external inspection dated 2026-01-18 (Doc D11) which identified moderate corrosion on the lower shell course of V-204. Work order raised to grit-blast affected area, apply protective coating, and carry out localised weld repair on thinned section. Requires hot work permit and confined-space precautions before execution.
Parts / Materials Used
Protective epoxy coating (18L), welding electrodes (E7018, 4mm) x 12, grit blasting media 40kg
Notes
Repair required scaffold erection at shell base; see Near-Miss Report D18 for a scaffold stability incident logged during this work. Subsequent OISD-105 internal audit (D22, 2026-06-10) noted the documentation trail linking this work order to the original inspection was not filed within the required timeframe — flagged as a compliance gap.